## Cover
Healthy Leaves
Prepared By:
Team 2
Daniel‌ ‌Savin‌ ‌-‌ ‌40010051‌ ‌
Karl‌ ‌Noory‌ ‌-‌ ‌40059592‌ ‌
Thomas‌ ‌Tran‌ ‌-‌ ‌4009564‌ ‌
Vicentiu-Cristian‌ ‌Badea‌ ‌-‌ ‌40027683‌ ‌
Jun‌ ‌Young‌ ‌Kim‌ ‌-‌ ‌40063176‌

## Backlog
Legend
A | Admin
C | Computer
E | Electrical
S | Software
Done
WIP
Story ID | Story Title | Card | Points | Sprint | Status | Conversation | Confirmation | Notes
S-10 | Firebase Connection | As a user I want to receive new data from the cloud. | 3 | 1 | Done | We should be able to connect to Firebase from an Android plantform to get data that is logged in there. | 1. Can we authenticate in the Firebase? 2. Is the app connected to Firebase?
S-14 | Plant Profiles | As a user I want to create and access various plant profiles so that I can differentiate between different plants. | 4 | 1 | Done | User should be able to differentiate their plants through different profiles. | 1. Can the user create a plant profile? 2. Can the user save a name in a plant profile? 3. Can the user access plant profiles? 4. Can the user the the list of plant profiles?
A-1 | Sprint 2 Plan | As a user I want to see new upcoming features so that I am interested in the product. | 4 | 1 | Done | We are graded on the Sprint 2 plan so this task is pretty obvious. To make sure project goes forward, everyone must know what to do. | 1. Does each team member knows what to do in Sprint 2? 2. Is the sprint 2 document complete?
A-2 | Obtain Module | As a user I want to have a device that works with WiFi so that I don't have to use a wire to get data. | 1 | 1 | Done | We need a microcontroller to perform data analysis of sensor data as well as a WiFi module to send that data to Firebase. | 1. Do we have a microcontroller that is working? 2. Do we have WiFi module with Firebase libraries available?
A-4 | Sprint 1 Testing Doc | As a user I want to see a testing document so that all possible sources of bugs are thought about and eliminated. | 5 | 1 | Done | We need to make sure that every feature that is planned and executed is working well. If something doesn't work, it is not complete. If the app crashed something is wrong. Therefore we try to break the app and its features so we can fix them. This is to make sure that the customer gets the best experience. | 1. Can we verify all the requirements? 2. Can we break down the app somehow?
A-5 | Sprint 1 Design Doc | As a user I want to have a design document so that the project description is available in a readable format. | 5 | 1 | Done | The design document is an important description of the whole project. It has all the relevant information in a readable format (compared to backlog, for example). | 1. Does the design document contain all the infomation about the project? 2. Is it submitted?
C-1 | Moisture Level | As a user I want to know the plant moisture levels (i.e. open app and see values) so that I know when water the plant. | 4 | 2 | Done | Moisture level of the soil is one of the most important things for a plant. Too much moisture leads to mold and rot development; too little leads to withering. | 1. Can the information from the moisture sensor be read? 2. Is the information sensible? 3. Is the information sent to Firebase?
S-1 | Moisture Notification | As a user I want to receive a notification when the soil is too dry/wet so that I water/don't water my plant to keep it healthy. | 4 | 2 | Done | To make sure that the plant stays healthy, the user must water it properly. When the moisture is too low, the user shall be notified. | 1. Does the user get a notification to water a plant when the moisture is too low? 2. Does the user get a notification when the soil is too moist?
S-15 | Plant Research | As a user I want to the database to have predefined data values that are correct, so that I don't kill my plants. | 4 | 2 | Done | We need to reseach various plant types and their needs to create a database. In addition we should look into making our own database or take data from someone else. | 1. Do we have a knowledge of most populat potted plants? 2. Do we have quantifiable knowledge of moisture, light levels, and temperature range for each type?
A-3 | Obtain Moisture Sensor | As a user I want to have a moisture sensor so that I can obtain moisture data. | 1 | 2 | Done | We need to obtain a moisture sensor to get soil moisture data. | 1. Do we have a sensor that is compatible with the microcontroller? 2. Can we obtain sensible data from it?
A-8 | Sprint 3 Plan | As a user I want to create Sprint 3 Plan so that there are new documented delivrables. | 4 | 2 | Done | We are graded on the Sprint 3 plan so this task is pretty obvious. To make sure project goes forward, everyone must know what to do. | 1. Does each team member knows what to do in Sprint 3? 2. Is the sprint 3 document complete?
A-9 | Sprint 2 Testing Doc | As a user I want to have a testing document so that the requirement satisfaction is verified and the possible bugs are detected. | 5 | 2 | Done | We need to make sure that every feature that is planned and executed is working well. If something doesn't work, it is not complete. If the app crashed something is wrong. Therefore we try to break the app and its features so we can fix them. This is to make sure that the customer gets the best experience. | 1. Can we verify all the requirements? 2. Can we break down the app somehow?
A-10 | Sprint 2 Design Doc | As a user I want to have a design document so that the project description is available in a readable format. | 5 | 2 | Done | The design document is an important description of the whole project. It has all the relevant information in a readable format (compared to backlog, for example). | 1. Does the design document contain all the infomation about the project? 2. Is it submitted?
S-20 | Main Folder Refactoring | As a user I want to have proper naming of the project folders and classes so that the project doesn't bug. | 2 | 2 | Done | Refactoring project directory, because the naming convention is confusing and causes bugs and app crashes. | 1. Is the project naming okay and the app compile? 2. Can team members understand the purpose of all classes?
E-4 | Device Size | As a user I want to have a device that does not occupy more place than a normal plant pot so that the overall design of my living space is not affected. | 2 | 2 | Done | The device should be as small as possible so the aesthetics of the plant are put forward. | 1. Does the device contribute to the aesthetics of the plant-pot enseble in a positive way?
C-2 | Light Level | As a user I want to know the plant light levels so that I can see whether the plant has enough light. | 4 | 2 | Done | Light exposure is also an important metric for plants, since it is required for photosynthesis. However, too much light can kill certain plants. | 1. Can the information from the light sensor be read? 2. Is the information sensible? 3. Is the information sent to Firebase?
C-3 | Temperature Level | As a user I want to know the plant temperature levels so that I can see whether the environment is too cold or hot for the plant. | 4 | 2 | Done | Temperature levels are important, because different plants grow in different regions. Generally plants live in a certain temperature range, depending on their genus. | 1. Can the information from the temperature sensor be read? 2. Is the information sensible? 3. Is the information sent to Firebase?
E-2 | Charging | As a user I want to charge my device so that it keeps working. | 5 | 2 | To do | The system uses power to work, and therefore should be recharged. The user should be able to charge the device. | 1. Can the user plug in a charging cable in the device? 2. Does the battery get charged? | Charger built in the SparkFun ESP32 Thing.
S-11 | Firebase: Read Moisture | As a user I want to receive data concerning moisture sensor so that I can get it on my app. | 8 | 3 | WIP | Once connected to Firebase, the app should obtain data values for moisture. | 1. Can the app obtain the data values for moisture form the Firebase? 2. Can the data values be logged in the app?
S-16 | Database | As a user I want to access multiple tables of various plant types so that I can have references for values. | 13 | 3 | WIP | Once data is known, we should decide how to implement the database: 1. make out own 2. use someone elses. | 1. Do we have an accessible database of various plants with their quantifiable information? 2. Can we access the database?
S-17 | Moisture Interface | As a user I want to see the current and the past moisture levels so that I can adjust my watering routine. | 8 | 3 | To do | The user should be able to see the moisture levels to either water the plant preventively or to see how he or she can modify their routine. While notifications are important, it is better not to reach a point when the soil is too dry or moist. | 1. Can the user access current level of moisture on the app? 2. Can the user see previous moisture levels? 3. Can the user see the graphical representation of moisture levels over time?
E-1 | Power | As a user I want to turn on/off the device so that I can choose when to use its battery. | 2 | 3 | To do | To save power when the system is not needed, the user should have control on the system's state. For safety, the user should also turn the system off when working with the pot. | 1. Can the user easily access a switch that turns on/off the system? 2. Can the user see the on/off state of the system?
A-11 | Sprint 3 Testing Doc | As a user I want to have a testing document so that the requirement satisfaction is verified and the possible bugs are detected. | 5 | 3 | To do | We need to make sure that every feature that is planned and executed is working well. If something doesn't work, it is not complete. If the app crashed something is wrong. Therefore we try to break the app and its features so we can fix them. This is to make sure that the customer gets the best experience. | 1. Can we verify all the requirements? 2. Can we break down the app somehow?
A-12 | Sprint 3 Design Doc | As a user I want to have a design document so that the project description is available in a readable format. | 2 | 3 | To do | The design document is an important description of the whole project. It has all the relevant information in a readable format (compared to backlog, for example). | 1. Does the design document contain all the infomation about the project? 2. Is it submitted?
S-21 | Sprint 3 Software Testing | As an user I want to make sure that everything is tested so that I don't have bugs. | 5 | 3 | To do | Testing is an integral part of development process. It allows us to test our code to see whether it can work properly. If it doesn't, bugs will appear in further iterations. | 1. Are there ways to break the software from the user side? 2. Are all aspects of code tested?
C-4 | Sprint 4 Hardware Testing | As an user I want to make sure that everything is tested so that I don't have bugs. | 5 | 3 | To do | Hardware testing is even more important than the software testing since software can be updated distantly. If something breaks or stops working, we will have to recall the product and replace it with it with a new one or a monetary compensation. This should not happen. | 1. Are there ways to break the hardware from the user side? 2. What can go wrong with hardware?
A-13 | Financial Analysis | As a user I want to know at what price the product should be sold so that I can see whether it fits in my budget. | 5 | 3 | To do | It is important to understand what is the cost of our product. Given the sunk and variable costs a price can be established. Given that price, we can see whether users will buy the product, given interview results. | 1. What is the final cost of hardware? 2. What are the R&D costs? 3. What price will the device be? 4. Is the device at a price people will buy it?
A-6 | Obtain Light Sensor | As a user I want to have a light sensor so that I can obtain light exposure data from the device. | 1 | 3 | To do | We need to obtain a light exposure sensor to get soil moisture data. | 1. Do we have a sensor that is compatible with the microcontroller? 2. Can we obtain sensible data from it?
A-7 | Obtain Temperature Sensor | As a user I want to have a temperature sensor so that I can obtain temperature data from the device. | 1 | 3 | To do | We need to obtain a temperature sensor to get soil moisture data. | 1. Do we have a sensor that is compatible with the microcontroller? 2. Can we obtain sensible data from it?
S-2 | Light Notification | As a user I want to receive a notification when the light levels are too low/high so that I move my plant to a better place in the house. | 2 | 4 | To do | To make sure the plant gets proper light exposure, the user must choose a good place for the plant pot. When there is not enough or too much light the user shall be notified. | 1. Does the user get a notification when the light levels are not proper?
S-3 | Temperature Notification | As a user I want to receive a notification when the temperature levels are too low/high so that I change the temperature of the room, or move it to another room. | 2 | 4 | To do | To make sure the plant exists in proper temperature range, the user must keep proper temperature in the area. When the temperature is not appropriate, the user shall be notified. | 1. Does the user get a notification to when the temperature is too low? 2. Does the user get a notification to when the temperature is too high?
E-5 | Environmental Resistance | As a user I want to have a device working in various environmental conditions so that I can install the device for outside plants. | 5 | 4 | To do | Plant owners may grow plants outdoors, thus it is preferrable that the device does not break down when face with outside envrionment. | 1. Does the device keep working when put outside? 2. How long does it take to break down given that it constantly rains?
S-4 | Recommendations | As a user I want to receive recommendation on healthier practices for the plant so that my plant stays healthy. | 5 | 4 | To do | There are many hints & tips out there for plant owners; it's always good to give users some ideas. | 1. Does the user get tips inside the app? 2. Do the tips change?
S-6 | Plant Identification | As a user I want to identify my plant with a picture so that I can understand it better. | 5 | 4 | To do | Some plant owners don't remember the name of their plant or don't know it. It is nice to have a possibility to for the user to determine what is the plant, so he/she can link it to the database. Using a google lense API. | 1. Can the user take a picture form the app? 2. Does the app determine the plants' name based on the picture? | Is there an API that can do it? If not, can we even do it?
E-3 | Rugged Design | As a user I want to have a device that it low maintenance so that I don't have to spend my time repairing it. | 5 | 4 | To do | The device must be sturdy and not breakdown easily. | 1. Can the device survive 1 meter fall? 2. Can the device be inserted in soil without breaking?
S-7 | Notification Recurrency | As a user I want to configure how often I receive the notifications so that the app is more adapted to my lifestyle. | 8 | 4 | To do | The user should be able to choose how often the app notifies them. | 1. Can the user go to options and change notification time range? 2. Does notification frequency change based on user preferences?
S-8 | Leaves and Pot Notification | As a user I want to receive reminders to cut leaves and repot the plant so that the plant growth is controlled. | 3 | 4 | To do | Some plants require pruning, and most plants require repotting. If a plant is not repotted, the root system may overgrow, killing the plant. | 1. Is there a notification to cut leaves, based on the amount of time passed since last pruning? 2. Is there a notification to repot the plant since last repotting? | Merged in S-5: Pot Notification.
S-9 | Plant Database Link | As a user I want to access plant database where I can link my plant to existing plant models so that I can get specific information on how to take care of my plant. | 5 | 4 | To do | Each users plant should be linked to a plant in a database so that the app has reference to the desired levels of moisture, light exposure and temperature range. | 1. Can the user access a dropdown list of various plants in the plant profile? 2. Can the user choose a plant type? 3. Does the profile get reference levels for all three metrics based on plant type chosen?
S-12 | Firebase: Read Light | As a use I want to receive data concerning light sensor so that I can get it on my app. | 2 | 4 | To do | Once connected to Firebase, the app should obtain data values for light. | 1. Can the app obtain the data values for light form the Firebase? 2. Can the data values be logged in the app?
S-13 | Firebase: Read Temperature | As a user I want to receive data concerning temperature sensor so that I can get it on my app. | 2 | 4 | To do | Once connected to Firebase, the app should obtain data values for temperature. | 1. Can the app obtain the data values for temperature form the Firebase? 2. Can the data values be logged in the app?
S-18 | Light Interface | As a user I want to see the current and the past light exposure levels so that I can see what spots are best in my home. | 3 | 4 | To do | The user should be able to see the light levels to see how much sunlight the plant gets during the day. | 1. Can the user access current light levels on the app? 2. Can the user see previous light levels? 3. Can the user see the graphical representation of the light levels over time?
S-19 | Temperature Interface | As a user I want to see the current and the past temperature levels so that I can adjust the temperature so the plants grow better. | 3 | 4 | To do | The user should be able to see the temeprature levels over time, so they can adjust it to optimal levels. | 1. Can the user access current temperature on the app? 2. Can the user see previous temeperature levels? 3. Can the user see the graphical representation of temperature levels over time?

## Completed items
Legend | [5 empty] | Sprint | Velocity | Notes
A | Admin |  |  |  |  | Sprint 1 | 26
C | Computer |  |  |  |  | Sprint 2 | 51 | Database (S3) incomplete
E | Electrical |  |  |  |  | Sprint 3 | 76
S | Software
Done
WIP
Story ID | Story Title | Card | Points | Sprint | Status | Conversation | Confirmation | Notes
S-10 | Firebase Connection | As a user I want to receive new data from the cloud. | 3 | 1 | Done | We should be able to connect to Firebase from an Android plantform to get data that is logged in there. | 1. Can we authenticate in the Firebase? 2. Is the app connected to Firebase?
S-14 | Plant Profiles | As a user I want to create and access various plant profiles so that I can differentiate between different plants. | 4 | 1 | Done | User should be able to differentiate their plants through different profiles. | 1. Can the user create a plant profile? 2. Can the user save a name in a plant profile? 3. Can the user access plant profiles? 4. Can the user the the list of plant profiles?
A-1 | Sprint 2 Plan | As a user I want to see new upcoming features so that I am interested in the product. | 4 | 1 | Done | We are graded on the Sprint 2 plan so this task is pretty obvious. To make sure project goes forward, everyone must know what to do. | 1. Does each team member knows what to do in Sprint 2? 2. Is the sprint 2 document complete?
A-2 | Obtain Module | As a user I want to have a device that works with WiFi so that I don't have to use a wire to get data. | 1 | 1 | Done | We need a microcontroller to perform data analysis of sensor data as well as a WiFi module to send that data to Firebase. | 1. Do we have a microcontroller that is working? 2. Do we have WiFi module with Firebase libraries available?
A-4 | Sprint 1 Testing Doc | As a user I want to see a testing document so that all possible sources of bugs are thought about and eliminated. | 5 | 1 | Done | We need to make sure that every feature that is planned and executed is working well. If something doesn't work, it is not complete. If the app crashed something is wrong. Therefore we try to break the app and its features so we can fix them. This is to make sure that the customer gets the best experience. | 1. Can we verify all the requirements? 2. Can we break down the app somehow?
A-5 | Sprint 1 Design Doc | As a user I want to have a design document so that the project description is available in a readable format. | 5 | 1 | Done | The design document is an important description of the whole project. It has all the relevant information in a readable format (compared to backlog, for example). | 1. Does the design document contain all the infomation about the project? 2. Is it submitted?
C-1 | Moisture Level | As a user I want to know the plant moisture levels (i.e. open app and see values) so that I know when water the plant. | 4 | 2 | Done | Moisture level of the soil is one of the most important things for a plant. Too much moisture leads to mold and rot development; too little leads to withering. | 1. Can the information from the moisture sensor be read? 2. Is the information sensible? 3. Is the information sent to Firebase?
S-1 | Moisture Notification | As a user I want to receive a notification when the soil is too dry/wet so that I water/don't water my plant to keep it healthy. | 4 | 2 | Done | To make sure that the plant stays healthy, the user must water it properly. When the moisture is too low, the user shall be notified. | 1. Does the user get a notification to water a plant when the moisture is too low? 2. Does the user get a notification when the soil is too moist?
S-15 | Plant Research | As a user I want to the database to have predefined data values that are correct, so that I don't kill my plants. | 4 | 2 | Done | We need to reseach various plant types and their needs to create a database. In addition we should look into making our own database or take data from someone else. | 1. Do we have a knowledge of most populat potted plants? 2. Do we have quantifiable knowledge of moisture, light levels, and temperature range for each type?
A-3 | Obtain Moisture Sensor | As a user I want to have a moisture sensor so that I can obtain moisture data. | 1 | 2 | Done | We need to obtain a moisture sensor to get soil moisture data. | 1. Do we have a sensor that is compatible with the microcontroller? 2. Can we obtain sensible data from it?
A-8 | Sprint 3 Plan | As a user I want to create Sprint 3 Plan so that there are new documented delivrables. | 4 | 2 | Done | We are graded on the Sprint 3 plan so this task is pretty obvious. To make sure project goes forward, everyone must know what to do. | 1. Does each team member knows what to do in Sprint 3? 2. Is the sprint 3 document complete?
A-9 | Sprint 2 Testing Doc | As a user I want to have a testing document so that the requirement satisfaction is verified and the possible bugs are detected. | 5 | 2 | Done | We need to make sure that every feature that is planned and executed is working well. If something doesn't work, it is not complete. If the app crashed something is wrong. Therefore we try to break the app and its features so we can fix them. This is to make sure that the customer gets the best experience. | 1. Can we verify all the requirements? 2. Can we break down the app somehow?
A-10 | Sprint 2 Design Doc | As a user I want to have a design document so that the project description is available in a readable format. | 5 | 2 | Done | The design document is an important description of the whole project. It has all the relevant information in a readable format (compared to backlog, for example). | 1. Does the design document contain all the infomation about the project? 2. Is it submitted?
S-20 | Main Folder Refactoring | As a user I want to have proper naming of the project folders and classes so that the project doesn't bug. | 2 | 2 | Done | Refactoring project directory, because the naming convention is confusing and causes bugs and app crashes. | 1. Is the project naming okay and the app compile? 2. Can team members understand the purpose of all classes?
E-4 | Device Size | As a user I want to have a device that does not occupy more place than a normal plant pot so that the overall design of my living space is not affected. | 2 | 2 | Done | The device should be as small as possible so the aesthetics of the plant are put forward. | 1. Does the device contribute to the aesthetics of the plant-pot enseble in a positive way?
C-2 | Light Level | As a user I want to know the plant light levels so that I can see whether the plant has enough light. | 4 | 2 | Done | Light exposure is also an important metric for plants, since it is required for photosynthesis. However, too much light can kill certain plants. | 1. Can the information from the light sensor be read? 2. Is the information sensible? 3. Is the information sent to Firebase?
C-3 | Temperature Level | As a user I want to know the plant temperature levels so that I can see whether the environment is too cold or hot for the plant. | 4 | 2 | Done | Temperature levels are important, because different plants grow in different regions. Generally plants live in a certain temperature range, depending on their genus. | 1. Can the information from the temperature sensor be read? 2. Is the information sensible? 3. Is the information sent to Firebase?
E-2 | Charging | As a user I want to charge my device so that it keeps working. | 5 | 2 | To do | The system uses power to work, and therefore should be recharged. The user should be able to charge the device. | 1. Can the user plug in a charging cable in the device? 2. Does the battery get charged? | Charger built in the SparkFun ESP32 Thing.
S-11 | Firebase: Read Moisture | As a user I want to receive data concerning moisture sensor so that I can get it on my app. | 8 | 3 | WIP | Once connected to Firebase, the app should obtain data values for moisture. | 1. Can the app obtain the data values for moisture form the Firebase? 2. Can the data values be logged in the app?
S-16 | Database | As a user I want to access multiple tables of various plant types so that I can have references for values. | 13 | 3 | WIP | Once data is known, we should decide how to implement the database: 1. make out own 2. use someone elses. | 1. Do we have an accessible database of various plants with their quantifiable information? 2. Can we access the database?
S-17 | Moisture Interface | As a user I want to see the current and the past moisture levels so that I can adjust my watering routine. | 8 | 3 | To do | The user should be able to see the moisture levels to either water the plant preventively or to see how he or she can modify their routine. While notifications are important, it is better not to reach a point when the soil is too dry or moist. | 1. Can the user access current level of moisture on the app? 2. Can the user see previous moisture levels? 3. Can the user see the graphical representation of moisture levels over time?
E-1 | Power | As a user I want to turn on/off the device so that I can choose when to use its battery. | 2 | 3 | To do | To save power when the system is not needed, the user should have control on the system's state. For safety, the user should also turn the system off when working with the pot. | 1. Can the user easily access a switch that turns on/off the system? 2. Can the user see the on/off state of the system?
A-11 | Sprint 3 Testing Doc | As a user I want to have a testing document so that the requirement satisfaction is verified and the possible bugs are detected. | 5 | 3 | To do | We need to make sure that every feature that is planned and executed is working well. If something doesn't work, it is not complete. If the app crashed something is wrong. Therefore we try to break the app and its features so we can fix them. This is to make sure that the customer gets the best experience. | 1. Can we verify all the requirements? 2. Can we break down the app somehow?
A-12 | Sprint 3 Design Doc | As a user I want to have a design document so that the project description is available in a readable format. | 2 | 3 | To do | The design document is an important description of the whole project. It has all the relevant information in a readable format (compared to backlog, for example). | 1. Does the design document contain all the infomation about the project? 2. Is it submitted?
S-21 | Sprint 3 Software Testing | As an user I want to make sure that everything is tested so that I don't have bugs. | 5 | 3 | To do | Testing is an integral part of development process. It allows us to test our code to see whether it can work properly. If it doesn't, bugs will appear in further iterations. | 1. Are there ways to break the software from the user side? 2. Are all aspects of code tested?
C-4 | Sprint 4 Hardware Testing | As an user I want to make sure that everything is tested so that I don't have bugs. | 5 | 3 | To do | Hardware testing is even more important than the software testing since software can be updated distantly. If something breaks or stops working, we will have to recall the product and replace it with it with a new one or a monetary compensation. This should not happen. | 1. Are there ways to break the hardware from the user side? 2. What can go wrong with hardware?
A-13 | Financial Analysis | As a user I want to know at what price the product should be sold so that I can see whether it fits in my budget. | 5 | 3 | To do | It is important to understand what is the cost of our product. Given the sunk and variable costs a price can be established. Given that price, we can see whether users will buy the product, given interview results. | 1. What is the final cost of hardware? 2. What are the R&D costs? 3. What price will the device be? 4. Is the device at a price people will buy it?
A-6 | Obtain Light Sensor | As a user I want to have a light sensor so that I can obtain light exposure data from the device. | 1 | 3 | To do | We need to obtain a light exposure sensor to get soil moisture data. | 1. Do we have a sensor that is compatible with the microcontroller? 2. Can we obtain sensible data from it?
A-7 | Obtain Temperature Sensor | As a user I want to have a temperature sensor so that I can obtain temperature data from the device. | 1 | 3 | To do | We need to obtain a temperature sensor to get soil moisture data. | 1. Do we have a sensor that is compatible with the microcontroller? 2. Can we obtain sensible data from it?
S-2 | Light Notification | As a user I want to receive a notification when the light levels are too low/high so that I move my plant to a better place in the house. | 2 | 4 | To do | To make sure the plant gets proper light exposure, the user must choose a good place for the plant pot. When there is not enough or too much light the user shall be notified. | 1. Does the user get a notification when the light levels are not proper?
S-3 | Temperature Notification | As a user I want to receive a notification when the temperature levels are too low/high so that I change the temperature of the room, or move it to another room. | 2 | 4 | To do | To make sure the plant exists in proper temperature range, the user must keep proper temperature in the area. When the temperature is not appropriate, the user shall be notified. | 1. Does the user get a notification to when the temperature is too low? 2. Does the user get a notification to when the temperature is too high?
S-6 | Plant Identification | As a user I want to identify my plant with a picture so that I can understand it better. | 5 | 4 | To do | Some plant owners don't remember the name of their plant or don't know it. It is nice to have a possibility to for the user to determine what is the plant, so he/she can link it to the database. Using a google lense API. | 1. Can the user take a picture form the app? 2. Does the app determine the plants' name based on the picture? | Is there an API that can do it? If not, can we even do it?
S-7 | Notification Recurrency | As a user I want to configure how often I receive the notifications so that the app is more adapted to my lifestyle. | 8 | 4 | To do | The user should be able to choose how often the app notifies them. | 1. Can the user go to options and change notification time range? 2. Does notification frequency change based on user preferences?
S-9 | Plant Database Link | As a user I want to access plant database where I can link my plant to existing plant models so that I can get specific information on how to take care of my plant. | 5 | 4 | To do | Each users plant should be linked to a plant in a database so that the app has reference to the desired levels of moisture, light exposure and temperature range. | 1. Can the user access a dropdown list of various plants in the plant profile? 2. Can the user choose a plant type? 3. Does the profile get reference levels for all three metrics based on plant type chosen?
S-12 | Firebase: Read Light | As a use I want to receive data concerning light sensor so that I can get it on my app. | 2 | 4 | To do | Once connected to Firebase, the app should obtain data values for light. | 1. Can the app obtain the data values for light form the Firebase? 2. Can the data values be logged in the app?
S-13 | Firebase: Read Temperature | As a user I want to receive data concerning temperature sensor so that I can get it on my app. | 2 | 4 | To do | Once connected to Firebase, the app should obtain data values for temperature. | 1. Can the app obtain the data values for temperature form the Firebase? 2. Can the data values be logged in the app?
S-18 | Light Interface | As a user I want to see the current and the past light exposure levels so that I can see what spots are best in my home. | 3 | 4 | To do | The user should be able to see the light levels to see how much sunlight the plant gets during the day. | 1. Can the user access current light levels on the app? 2. Can the user see previous light levels? 3. Can the user see the graphical representation of the light levels over time?
S-19 | Temperature Interface | As a user I want to see the current and the past temperature levels so that I can adjust the temperature so the plants grow better. | 3 | 4 | To do | The user should be able to see the temeprature levels over time, so they can adjust it to optimal levels. | 1. Can the user access current temperature on the app? 2. Can the user see previous temeperature levels? 3. Can the user see the graphical representation of temperature levels over time?

## Sprint 1
Goal: Create a local and remote database of plants, that the user can interact with in order to organize a list of plants, and post data with embedded system to the remote server.
Story ID | Task Id | Title | Task Description | Time | Status | By | Notes
S-10 | S-10.1 | Notification | Create notification in the app. | 2 | Done | Vily | The application allows in app notifications for testing purposes
| S-10.2 | Create Firebase Link | Create a connection to firebase database | 2 | Done | Vily | The application now contains all prerequisite connections to the Firebase database
| S-10.3 | Push notification | Create push notification for specific users, given token | 2 | Done | Vily | Push notifications were created and tested on specified users
| S-10.4 | Authentication | Create Firebase authentication service. | 2 | Done | Vily | Users can register with an email and password, saving it to the Firebase database
| S-10.5 | Link App to Firebase | Link the app project to the Firebase database. | 2 | Done | Vily | The app can communicate with the Firebase database to retrieve and save user token
S-14 | S-14.1 | Profile | Create a plant profile containing name, watering interval, light exposure, temperature and growth. | 5 | Done | Jun
| S-14.2 | Display Watering | Display recommended moisture levels. | 1 | Done | Jun
| S-14.3 | Display Light | Display recommended light levels. | 1 | Done | Jun
| S-14.4 | Display Temperature | Display recommended temperature. | 1 | Done | Jun
| S-14.5 | Display Growth | Display how often to prune and to repot. | 1 | WIP | Jun
| S-14.6 | Plant ListView | Create a a list of all plant profiles with an option to create a new one. | 5 | Done | Jun
C-1 | C-1.1 | Setup | Setup a microcontroller with the WiFi module. | 1 | Done | Karl | Note: mock data was used. Moisture sensor will be verified once we get it.
| C-1.2 | Translate Data | Analyze incoming data and translate it to sensible values (0-100% moisture). | 1 | WIP | Karl
| C-1.3 | Send Data | Send the resulting data to the Firebase. | 5 | Done | Karl
| C-1.4 | Receive Data | Get data from the Firebase. | 5 | Done | Karl | Dummy data was used.
A-1 | A-1.1 | Backlog Grooming | Remove redundant stories, remove useless stories, merge some stories, clean up the rest. | 5 | Done | Daniel | Given that the project started during midterms, the original backlog was rushed and had to be extensively groomed.
| A-1.2 | Sprint 1 Cleanup | Cleanup sprint 1 tasks. | 2 | Done | Daniel | Sprint 1 was unrealistic given exam period, and tasks were disjointed.
| A-1.3 | Sprint 1 and 2 Tasks | Meetup with team members to discuss the direction of the project and tasks completed as well as the tasks to do. | 3 | Done | Daniel | Karl - 0.5 hrs Vily - 0.5 hrs Jun - 0.5 hrs Thomas - 0.5 hrs
A-2 | A-2.1 | Find and Get | Choose a module from the ones given by Concordia and get them. | 1 | Done | Daniel
A-4 | A-4.1 | Software | Create test cases for software. | 5 | Done |  | Vily, Thomas and Jun
| A-4.2 | Hardware | Create test cases for hardware. | 5 | Done |  | Karl and Daniel
A-5 | A-5.1 | Wireframe | Create the Android wireframe for the project. | 2 | Done | Vily
| A-5.2 | System Architecture | Write down system architecture for the project. | 2 | Done | Vily
| A-5.3 | Hardware Architecture | Write down hardware architecture for the project. | 2 | Done |  | Daniel, Karl
| A-5.4 | Software Architecture | Write down software architecture for the project. | 2 | Done |  | Vily, Thomas
| A-5.5 | Use Cases | Write down the possible use cases. | 2 | Done | Vily
| A-5.6 | Testing | Write down the test plan. | 2 | Done |  | Vily, Jun
| A-5.7 | Appendix | Put additional information to the appendix. | 2 | Done |  | Daniel
S-16 | S-16.1 | Relational Database | Design a database with all its relations and attributes. | 3 | Done | Thomas | Create diagrams: ER and Database to illustrate the relationships of the database.
| S-16.2 | Firebase Database | Create template for team members by implementing first tuples for each table through Firebase console. | 2 | Done | Thomas
| S-16.3 | Plant Container Class | Implement Plant class. | 2 | Done | Thomas | Attributes: strings: name, description ints: moisture, light, temperature
| S-16.4 | Plant as Database Input | Implement an activity allowing users to add plant entities/tuples to the Plant table from the Firebase database. | 2 | Done | Thomas
| S-16.5 | Plant Write Firebase | Create cloud based database for the plant entities. | 5 | Done | Thomas | When given Plant object to the function, it is then added onto the Firebase database.
| S-16.6 | RecyclerView for Plant Tuples | Implement an activity that will display a RecyclerView list that will be populated by all the Plant tuples. | 5 | Done | Thomas | Use handler MyAdapter class that will populate the PlantDatabaseActivity.
| S-16.7 | Plant Read Firebase | On start of PlantDatabaseActivity RecyclerView gets populated with data read from Firebase database. | 5 | Done | Thomas | Every single tuple is read from the database and added to the Plant linkedlist. List sent as argument to myAdapter.
| S-16.8 | Merge | Merge App to Team Branch | 3 | Done | Thomas | Merge plant database features to the team branch.

## Sprint 2
Sprint 2 Goal: Fully integrate hardware and software through Firebase: we want to see moisture data from hardware on our app. To appropiatly store the moisture measurement data from the hardware to the app, user owned plants can be stored in the database.
Story ID | Task Id | Title | Task Description | Time | Status | By | Notes
C-1 | C-1.1 | Setup | Setup a microcontroller with the WiFi module and current time. | 5 | Done | Karl | Issues for Daniel: old router. [Karl and Daniel] Using UNIX time.
| C-1.2 | Calibrate | Analyze incoming data and translate it to sensible values (0-100% moisture). | 1 | Done | Daniel | 0% = air 100% = water
| C-1.3 | getMoisture() | Set up hardware and write a function reading and returning integer describing the % moisture. | 1 | Done | Daniel
| C-1.4 | getEpochTime() | Set up a function that takes time from a server and translates it to UNIX format at the time of sensor reading. | 2 | Done | Karl
| C-1.5 | Send Data | Send the resulting data with time to the Firebase. | 5 | Done | Karl | Impemented in Sprint 1.
| C-1.6 | Confirm | Get confirmation from Firebase. | 5 | Done | Karl | Implemented in Sprint 1.
| C-1.7 | Refactoring | Refactor writeToDatabase() | 2 | Done | Karl
C-2 | C-2.1 | Calibrate | Analyze incoming data and translate it to sensisble values (0-100& light). | 1 | Done | Karl | 0% = covered 100% = full sun
| C-2.2 | getLight() | Set up hardware and write a function reading and returning integer describing the % light. | 1 | Done | Karl
| C-2.3 | Send Data | Send the resulting data to the Firebase. | 1 | Done | Karl
| C-2.4 | Refactoring | Refactor the function. | 1 | Done | Daniel
C-3 | C-1.2 | Calibrate | Analyze incoming data and translate it to sensible values (0-100% moisture). | 1 | Done | Daniel | Karl - initial calibration: 0.5 Daniel - final calibration: 2
| C-1.3 | getTemperature() | Set up hardware and write a function reading and returning integer describing the % moisture. | 1 | Done | Karl
| C-1.4 | Send Data | Send the resulting data to the Firebase. | 1 | Done | Karl
| C-1.5 | Refactoring | Refactor the function. | 2 | Done | Daniel | SparkFun has different architecture from Arduino. "int" and "float" must be cast.
S-11 | S-11.1 | Read Data | Read and record data from the firebase. | 4 | Done | Thomas
| S-11.2 | Low Values | Verify if the values are low or high, given recommendations. | 1 | WIP | Thomas
S-1 | S-1.1 | Push Notification | Create a push notification for moisure level | 5 | Done | Vily | Frequency to set.
| S-1.2 | Cloud Function | Define cloud functions for Firebase. | 5 | Done | Vily
| S-1.3 | Trigger | Trigger defined cloud functions when user values are too low. | 5 | Done | Vily | Triggers on write.
| S-1.4 | Logout | Allow user to log out from his account. | 5 | Done | Vily
| S-1.5 | Sign-in | Allow the user to sign in with different credentials after opening the app. | 5 | Done | Vily
S-15 | S-15.1 | Plant Types | Research various plant types. | 5 | Done | Jun
| S-15.2 | Plant Needs | Based on previous task, find what each type of plant needs. | 5 | Done | Jun
| S-15.3 | Quantification | Quantify the plant needs to numbers that we can work with. | 5 | Done | Jun
S-16 | S-16.9 | Fill | Fill the database with found and/or calculated values. | 5 | Done | Jun
| S-16.10 | Edit Database | Implement a frontend edit function to database entries to modify their attributes. | 3 | Done | Thomas
| S-16.11 | Edit Tuples | Given a plantID, edit Plant tuples from the database. | 5 | Done | Thomas | editPlantDatabaseActivity receives an Intent to know on which tuple the edit should be done.
| S-16.12 | add userPlant | Implement an activity that lets user add a plant from the catalog to their own | 3 | Done | Thomas
| S-16.13 | store userPlants in database | Create OwnsA relationships in the database through the client application | 5 | Done | Thomas
| S-16.14 | display user's plants in a list | Display all user plants in a list and each item has an onClick that directs to a detailed page on the plant | 5 | Done | Thomas
| S-16.15 | Get userPlant Profile | Using the token generated by authentication, the userPlant object gets all the attributes of the plant. | 2 | Done | Thomas
| S-16.16 | Get Matching Plant Profile | Using the same token, attributes of the plant that matches the plant owned by the user can be stored in a Plant object. | 2 | Done | Thomas
| S-16.17 | Compare Attributes | Compare userPlan data to the database plant recommendations. | 2 | WIP | Thomas | Redundant to S-11.2; once S-11.2 is done, this one should be done.
| S-16.18 | Send Notification | Send notification if the difference is present. | 3 | To do
| S-16.19 | Store Pics | Upload pictures to database | 5 | To do |  | Sep to diff story
| S-16.20 | OwnsA Relationship | The user can post picture of its plant to the general database. | 5 | To do
A-3 | A-3.1 | Research | Find a moisture sensor that is within 10$ and that can read soil moisture. | 0.5 | Done | Daniel | Got one from Concordia.
| A-3.2 | Buy | Buy it. | 0.5 | Done | Daniel
| A-3.3 | Test | Test the sensor. | 1 | Done | Daniel | Test with the results of C-1 story tasks and setup.
| A-3.4 | Data Translation | Translate data from the sensor to some sensible value, confirming C-1.3. | 1 | Done | Daniel
E-4 | E-4.1 | Components | Choose internal components (MC, battery, etc.) | 5 | To do | Karl
| E-4.2 | PCB | Design PCB for given components. | 5 | Done | Karl | L,M,T -> P36,37,38
| E-4.3 | External | Design the external look of the device (a box) that will contain the internal components. | 5 | WIP | Karl
E-5 | E-5.1 | Material Choice | Research various materials that can withstand the outside environment. | 2 | To do
| E-5.2 | Apply to Design | Apply the selected material to the external hardware design, defined in E-4.3. | 1 | To do
S-20 | S-20.1 | Refactoring | Refactor the main folder, since naming conventions are creating bugs. | 4 | Done | Thomas
| S-20.2 | Debug Sprint 1 | Debug code that failed acceptance test. | 3 | Done | Thomas
A-8 | A-8.1 | Sprint 2 Scrum | Get feedback on tasks, and update the Sprint 2. | 2 | To do | Daniel | [Everyone]
| A-8.2 | Sprint 3 Plan | Meet with teammates and discuss what features will be implemented and what bugs should be fixed in Sprint 3. | 3 | To do | Daniel | [Everyone]
| A-8.3 | Backlog Grooming | Clean up and reorganize the backlog based on previous tasks. | 4 | To do | Daniel
A-9 | A-9.1 | Hardware | Write tests for hardware (new sensors mostly). | 3 | To do | Daniel
| A-9.2 | Test | Test the hardware. Light test, Moisture test, Temperature test | 3 | Done | Karl | Sprint 2 is critical; hardware should be working flawlessly, since software is the issue.
| A-9.3 | Software | Write tests for software. | 5 | To do |  | Jun, Vily, Thomas
| A-9.4 | DoD | Write Definition of Done for tasks. | 5 | To do | Jun
A-10 | A-10.1 | Wireframe | Update the Android wireframe for the project. | 1 | To do | Thomas
| A-10.2 | System Architecture | Update system architecture for the project. | 1 | To do | Vily
| A-10.3 | Hardware Architecture | Update hardware architecture for the project. | 1 | To do | Daniel
| A-10.4 | Software Architecture | Update software architecture for the project. | 4 | Done | Jun | Introduced parent-child relationship and organized hierarchy between activities.
| A-10.5 | Use Cases | Update the possible use cases. | 5 | To do
| A-10.6 | Testing | Write down the test plan. | 3 | To do
| A-10.7 | Finance | Determine the price of components. | 5 | To do
| A-10.8 | Appendix | Put additional information to the appendix. | 2 | To do
| A-10.9 | Introduction | Write down the intro. | 1 | Done | Daniel
Login,logout page
Register device activity
Alert user when wifi is off
|  |  |  | 2 | WIP | Thomas
unique user identification from Android to Arduino side
A-task document hardware
Delete plant option in plant profile page
Change app logo and name
|  | unique id |  |  |  | Karl
everyone connected to device will get notified
hardware side: create additional database write called ALERT[sensor] so Vily can read from it.
ADD TESTING AS A BACKLOG STORY

## Sprint 3
Sprint 3: The goal of this sprint is to implement temperature and light readings, as well as to graphically demonstrate all of the values over time period.
Story ID | Task Id | Title | Task Description | Time | Status | By | Notes
S-16 | S-16.17 | Compare Attributes | Compare userPlan data to the database plant recommendations. | 2 | Done | Thomas | Redundant to S-11.2; once S-11.2 is done, this one should be done ASAP. | Total hours: 120
| S-16.18 | Send Notification | Send notification if the difference is present. | 5 | To do | Vily | with Karl | Add value to product.
| S-16.19 | Store Pics | Upload pictures to database | 5 | To do | Thomas |  | Water my plant button
| S-16.20 | OwnsA Relationship | The user can post picture of its plant to the general database. | 5 | To do | Thomas |  | Final demo:
S-11 | S-11.2 | Low Values | Verify if the values are low or high, given recommendations. | 4 | Done | Thomas |  | 10-20 mins -> presentation/ppt what product does, value, etc
E-5 | E-5.1 | Material Choice | Research various materials that can withstand the outside environment. | 2 | Done | Karl |  | after: demo of product change env of sensor to demo how app changes, followed by questions and answers
| E-5.2 | Apply to Design | Apply the selected material to the external hardware design, defined in E-4.3. | 1 | To do | Karl |  | be prepared and practice for presentation
S-17 | S-17.1 | Recent Value | Get most recent value of moisture. | 2 | Done | Thomas
| S-17.2 | Click | Make recent value clickable, transferring me to the list of previous data. | 1.5 | Done | Jun
| S-17.3 | Update Data | Get all data that is new since last time it was checked. | 4 | To do | Thomas
| S-17.4 | Clean Up | Delete old data periodically. | 5 | To do | Jun
| S-17.5 | Graph | Display a graph of the logged data. | 5 | Done | Jun | with thomas actual duration 11 hours (jun 7, thomas 4)
S-21 | S-21.1 | Firebase Connection | Run and fix test cases from requirement ID S-10 | 4 | Done | Thomas
| S-21.2 | Plant Profile and Display | Run and fix test cases from requirement ID S-14 | 2 | Done | Thomas
| S-21.3 | Database | Run and fix test cases from requirement ID S-16 | 2 | Done | Thomas
| S-21.4 | Notifications | Run and fix test cases from requirement ID S-1 | 5 | WIP | Vily
E-1 | E-1.1 | Switch | Implement a hardware switch. | 2 | To do | Karl
| E-1.2 | PCB | Add switch to PCB. | 1 | To do | Karl | Add to the wiring diagram.
| E-1.3 | Drawing | Add switch to graphical design. | 1 | WIP | Karl
A-11 | A-11.1 | Hardware | Write tests for hardware (new sensors mostly). | 3 | To do | Daniel
| A-11.2 | Test | Test the hardware. Light test, Moisture test, Temperature test | 3 | To do | Karl
| A-11.3 | Software | Write tests for software. | 5 | To do |  | Vily & Thomas
| A-11.4 | DoD | Write Definition of Done for tasks. | 5 | To do | Jun
A-12 | A-12.1 | Wireframe | Update the Android wireframe for the project. | 1 | To do | Thomas
| A-12.2 | System Architecture | Update system architecture for the project. | 1 | To do | Daniel
| A-12.3 | Hardware Architecture | Update hardware architecture for the project. | 1 | To do | Karl
| A-12.4 | Software Architecture | Update software architecture for the project. | 4 | To do | Jun
| A-12.5 | Use Cases | Update the possible use cases. | 5 | To do |  | All
| A-12.6 | Testing | Write down the test plan. | 3 | To do | Daniel
| A-12.7 | Finance | Determine the price of components. | 5 | To do |  | Daniel & Karl
| A-12.8 | Appendix | Put additional information to the appendix. | 2 | To do | Daniel
| A-12.9 | Introduction | Write down the intro. | 1 | To do | Daniel
C-4 | C-4.1 | Hardware | Run and fix test cases from requirement ID C-1 | 5 | To do | Karl
A-13 | A-13.1 | Hardware Cost | Determine the cost of hardware. | 3 | Done | Karl
| C-4.3 | R&D Cost | Determine the cost of maintenance and development. | 3 | To do | Karl
| C-4.4 | Price | Find the optimal price based on previous interviews. | 4 | To do | Daniel
| C-4.5 | Market | Research market. | 5 | To do | Daniel
T | T-1 | re-calibrating plant info | re-calibrate the plant catalog info corresponding to the sensor data | 2 | Done | Thomas
| T-2 | User Experience | Application navigation and user interface improvements. Uniformisation and conformity of fonts, colors and styles. | 7 | Done | Thomas
| T-3 | Arduino Device App Pairing | Pairing the device with the app should be user friendly and can be done both ways | 3 | Done | Thomas
| T-5 | Real-time data | Light, moisture and temperature current values are updated in real time on the plant profile page | 2 | Done | Thomas
S-6 | S-1 | Libraries and flow | Set up tensor flow environment and install libraries/tools. | 3 | Done | Thomas
| S-2 | Training | Train a flower recognizer using Colab. | 2 | Done | Thomas
| S-3 | GPU Acceleration | Accelerate inference with GPU delegate. | 1 | Done | Thomas
| S-4 | Testing | Test performance and modify training accordingly to improve recognition. | 1 | Done | Thomas

## Timetable
Sprint 2 |  |  | Sprint 3
Member | Task | Time Spent | Member | Task | Time Spent | Sprint review
Jun | A-10.4 | 4 | Daniel | A-11.1 | 4 | Demo the sensor: | trigger notification
Daniel | A-3.1 | 0.5 | Daniel | A-12.2 | 2 |  | trigger change in data
Daniel | A-3.2 | 0.5 | Daniel | A-12.6 | 4 |  | no need to see Firebase
Daniel | A-3.3 | 2 | Daniel | A-12.8 | 2 |  | We try to SELL the product
Daniel | A-3.4 | 1 | Daniel | A-12.9 | 2 | Figure out unique codes and shit
Jun | S-15.1 | 1.5 | Daniel | C-4.4 | 4 | Testing to do during story completion
Jun | S-15.2 | 1.5 | Daniel | C-4.5 | 5 | Write docs as project goes
Jun | S-15.3 | 2 | Daniel | A-12.5 | 1
Jun | S-16.9 | 2 | Daniel | A-12.7 | 5
Thomas | S-16.10 | 5 | Jun | S-17.2 | 1.5 | `
Thomas | S-16.11 | 3 | Jun | S-17.4 | 5
Thomas | S-16.12 | 5 | Jun | S-17.5 | 7
Thomas | S-16.13 | 3 | Jun | A-11.4 | 5
Thomas | S-16.14 | 7 | Jun | A-12.4 | 4
Thomas | S-16.15 | 2 | Jun | A-12.5 | 1
Thomas | S-16.16 | 2 | Karl | E-5.1 | 2
Vily | S-1.1 | 5 | Karl | E-5.2 | 1
Vily | S-1.2 | 5 | Karl | E-1.1 | 2
Vily | S-1.3 | 8 | Karl | E-1.2 | 1
Vily | S-1.4 | 2 | Karl | E-1.3 | 1
Vily | S-1.5 | 2 | Karl | A-11.2 | 3
Daniel | A-10.9 | 1 | Karl | A-12.3 | 1
Karl | C-1.1 | 5 | Karl | C-4.1 | 5
Daniel | C-1.2 | 1 | Karl | A-13.1 | 3
Daniel | C-1.3 | 2 | Karl | C-4.3 | 3
Karl | C-1.4 | 3.5 | Karl | S-16.18 | 3
Karl | C-1.7 | 2 | Karl | A-12.5 | 1
Karl | C-2.1 | 0.5 | Karl | A-12.7 | 5
Karl | C-2.2 | 1 | Thomas | S-16.17 | 2
Karl | C-2.3 | 1 | Thomas | S-16.19 | 5
Daniel | C-2.4 | 1 | Thomas | S-16.20 | 5
Daniel | C-3.1 | 2 | Thomas | S-11.2 | 4
Karl | C-3.1 | 0.5 | Thomas | S-17.1 | 2
Karl | C-3.2 | 1 | Thomas | S-17.3 | 4
Karl | C-3.3 | 1 | Thomas | S-21.1 | 4
Daniel | C-3.4 | 2 | Thomas | S-21.2 | 2
Thomas | S-20.1 | 4 | Thomas | S-21.3 | 2
Thomas | S-20.2 | 3 | Thomas | A-12.1 | 1
Daniel | A-8.1 | 2 | Thomas | T-1 | 2
Karl | A-8.1 | 0.5 | Thomas | T-2 | 7
Thomas | A-8.1 | 0.5 | Thomas | T-3 | 3
Jun | A-8.1 | 0.5 | Thomas | T-5 | 2
Vily | A-8.1 | 0.5 | Thomas | S-1 | 3
Daniel | A-8.2 | 2 | Thomas | S-2 | 2
Karl | A-8.2 | 0.5 | Thomas | S-3 | 1
Thomas | A-8.2 | 0.5 | Thomas | S-4 | 1
Jun | A-8.2 | 0.5 | Thomas | A-11.3 | 1
Vily | A-8.2 | 0.5 | Thomas | S-17.5 | 4
Daniel | A-8.3 | 8 | Thomas | A-12.5 | 1
Thomas | S-11.1 | 4 | Vily | S-16.18 | 5
Thomas | S-20.1 | 6 | Vily | S-21.4 | 5
Thomas | S-20.2 | 2 | Vily | A-11.3 | 4
Thomas | A-10.1 | 2 | Vily | A-12.5 | 2
Daniel | A-9.1 | 2
Karl | A-9.2 | 3
Daniel | A-9.2 | 3
Thomas | A-9.3 | 1
Jun | A-9.4 | 4