## sprint1
Story ID | DoD | Confirmation | Validation
S-10 | Tested | Can the microcontroller connect to the Firebase Database? Can the user register to the Firebase Database? Can the application retrieve the user token? | Complete
S-16 | Tested | Do we have an accessible database of various plants with their quantifiable information? Do we have an accessible database of the user owned plants and their quantifiable accessible data log? Can we access the database? Can we post to the database? | Incomplete, the database doesn't establishes relationships between plants and users and therefore also don't hold quantifiable data log.
S-14 | Tested | Can the plant profile be saved locally? Can the plant profile be saved remotely? | Complete
A-1 | Deployable | Does each team member knows what to do in Sprint 2? Is the sprint 2 document complete? | Complete
A-2 | Deployable | Can my microcontroller connect to the WIFI given this module? | Complete
A-4 | Deployable | Can we verify all the requirements? Can we break down the app somehow? | Complete
A-5 | Deployable | Does the design document contain all the infomation about the project? Is it submitted? | Complete
C-1 | Have had a code review | Can the microcontroller read moisture levels? Is the data saved to the microcontroller? | Complete
have had a code review
tested
immediately deployable

## sprint2
Story ID: C-1
User Story: Moisture level
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Setup microcontroller with wifi module and current time | Complete
2. Calibrate incoming data and translate to sensible, usable information | Complete
3. Setup hardware and write function in software capable of reading and returning moisture levels | Complete
4. Setup function that takes time from server and translates it into UNIX format at the time of sensor reading | Complete
5. Send resulting data to firebase | Complete
6. Get confirmation from Firebase. | Complete
7. Refactor function writeToDatabase() | Complete
Story ID: C-2
User Story: Light level
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Calibrate incoming data and translate to sensible, usable information | Complete
2. Setup hardware and write function in software capable of reading and returning light levels | Complete
3. Send resulting data to firebase | Complete
4. Refactor function writeToDatabase() | Complete
Story ID: C-3
User Story: Temperature level
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Calibrate incoming data and translate to sensible, usable information | Complete
2. Setup hardware and write function in software capable of reading and returning temperature levels | Complete
3. Send resulting data to firebase | Complete
4. Refactor function writeToDatabase() | Complete
Story ID: S-15
User Story: Plant research
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Researched data peer reviewed - Sign off by product owner | Status
1. Research done on various types of houseplant | Complete
2. Obtain specific information relating to the ideal growth environment for each specific houseplant | Complete
3. Translate researched information into sensible, usable data | Complete
Story ID: S-16
User Story: Database
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Filling the realtime firebase database with plant types | Complete
2. Edit button to modify plant entries in catalog/firebase database | Complete
3. Edit tuples given plant ID | Complete
4. Implement activity that allows user to add a plant from the catalog into their own list | Complete
5. Implement list for user's plants with relationship in the database through client | Complete
6. Display user's plants in a list | Complete
7. Display individual plant profiles of the user's list | Complete
8. Getting matching plant profiles | Complete
9. Compare the data related to user plants with those in the catalog | WIP
10. Send notification to user if discrepancies are present between catalog plant info and user plant info | Incomplete
11. Upload pictures of plants to user's own database | Incomplete
12. Upload pictures of plants to general community database | Incomplete
Story ID: S-11
User Story: Firebase - Read moisture
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Sign off by product owner | Status
1. Read and record data from the firebase database | WIP
2. Verify if incoming data for user plants are too high/low compared to ideal plant data in the firebase database | WIP
Story ID: S-1
User Story: Moisture Notification
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Create a push notification for moisure level | Complete
2. Define cloud functions for Firebase | Complete
3. Trigger defined cloud functions when user values are too low | Complete
4. Allow user to log out from his account | Complete
5. Allow the user to sign in with different credentials after opening the app. | Complete
Story ID: A-3
User Story: Obtain Moisture Sensor
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Test document updated - Sign off by product owner | Status
1. Find a moisture sensor that is within 10$ and that can read soil moisture. | Not applicable
2. Buy motion sensor | Not applicable
3. Test moisture sensor | Complete
4. Translate incoming sensor data to sensible, usable information | Complete
Story ID: E-4
User Story: Device size
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Design document updated - Test document updated - Sign off by product owner | Status
1. Choose internal components (MC, battery, etc.) | Incomplete
2. Design PCB | Complete
3. Design external look of device to contain internal components | WIP
Story ID: E-5
User Story: Environmental resistance
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Design document updated - Test document updated - Research data peer reviewed - Sign off by product owner | Status
1. Research various materials that can withstand the outside environment | Incomplete
2. Apply the selected material to the external hardware design | Incomplete
Story ID: S-20
User Story: Main folder refactoring
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Refactor the main folder, since naming conventions are creating bugs | Complete
2. Debug code that failed acceptance test. | Complete
Story ID: A-8
User Story: Sprint 3 planning
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Design document updated - Test document updated - Project Backlog updated - Sprint 3 Backlog updated - Sprint velocity calculated - Sign off by product owner | Status
1. Get feedback on tasks, and update the Sprint 2. | Incomplete
2. Meet with teammates and discuss what features will be implemented and what bugs should be fixed in Sprint 3. | Incomplete
3. Clean up and reorganize the backlog based on previous tasks. | Incomplete
Story ID: A-9
User Story: Testing documentation
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Test document updated - Sign off by product owner | Status
1. Write tests for hardware (new sensors mostly). | Incomplete
2. Test the hardware. Light test, Moisture test, Temperature test | Complete
3. Write tests for software. | Complete
4. Write Definition of Done for tasks. | Complete
Story ID: A-10
User Story: Design documentation
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Design document updated - Sign off by product owner | Status
1. Update the Android wireframe for the project. | Incomplete
2. Update system architecture for the project. | Complete
3. Update hardware architecture for the project. | Incomplete
4. Update software architecture for the project. | Incomplete
5. Update the possible use cases. | Incomplete
6. Write down the test plan. | Incomplete
7. Determine the price of components. | Incomplete
8. Put additional information to the appendix. | Incomplete
9. Write down the intro. | Incomplete

## sprint3
Story ID: S-16
User Story: Database
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Compare attributes between sensor and ideal plant data | Complete
2. Send notifications if discrepancies are found between sensor data and ideal plant data | Complete
3. Uploading and storing pictures of plants in the database | Incomplete
4. User can post their personal plants on the database | Incomplete
Story ID: S-11
User Story: Firebase: read moisture
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Compare attributes between sensor and ideal plant data | Complete
Story ID: E-5
User Story: Environmental Resistance
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Research data peer reviewed - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Sign off by product owner | Status
1. Research various materials that can withstand outside conditions | Complete
2. Apply researched material to external hardware design | Complete
Story ID: S-17
User Story: Moisture Interface
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Obtaining most recent sensor data | Complete
2. Make recent data clickable to obtain listview of past values for that specific data | Complete
3. Update plant data | Complete
4. Periodically delete old data | Incomplete
5. Graphing all values for the specific data | Complete
Story ID: S-21
User Story: Sprint 3 software testing
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Integration test performed and passed - Design document updated - Test document updated - Code review complete - Code build with no error - Sign off by product owner | Status
1. Fixing test cases for firebase connection from S-10 | Complete
2. Fixing test cases for plant profile and display from S-14 | Complete
3. Fixing test cases for the database from S-16 | Complete
4. Fixing test cases for notifications from S-1 | Complete
Story ID: E-1
User Story: Power
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Design document updated - Sign off by product owner | Status
1. Implement hardware switch | Complete
2. Add switch to PCB | Complete
3. Add switch to graphical design | Complete
Story ID: A-11
User Story: Sprint 3 testing document
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Unit test performed and passed - Test document updated - Sign off by product owner | Status
1. Writing test case for hardware | Complete
2. Test the hardware. Light test, Moisture test, Temperature test | Complete
3. Writing test case for software | Complete
4. Write defitinion of done tasks | Complete
Story ID: A-10
User Story: Sprint 3 design document
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Design document updated - Sign off by product owner | Status
1. Update the Android wireframe for the project. | Complete
2. Update system architecture for the project. | Complete
3. Update hardware architecture for the project. | Complete
4. Update software architecture for the project. | Complete
5. Update the possible use cases. | Complete
6. Write down the test plan. | Complete
7. Determine the price of components. | Complete
8. Put additional information to the appendix. | Complete
9. Write down the intro. | Complete
Story ID: C-4
User Story: Hardware testing
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Test document updated - Sign off by product owner | Status
1. Fixing test case for hardware from C-1 | Complete
Story ID: A-13
User Story: Financial analysis
DoD Checklist for this PBI: - Requirements mentioned in PBI are satisfied - Research data peer reviewed - Sign off by product owner | Status
1. Determine cost of hardware | Complete
2. Determine cost of maintenance and development | Complete
3. Find optimal price based on interviews | Complete
4. Research market opporunities | Complete